## Sheet1
Current status of Alma License Task Force recommendations |  | 2016-09-27
Items in green are considered the most important issues at this point by task force members
Recommendation | Status | Notes from the Task Group | Ex Libris Response | Relevant SalesForce cases | 21-08-2016 EXL Note
Record Structure
Signed by” field should not have to be populated from the user database as this fields needs to be stable. | Released as part of March 2015 release | now working as needed
Linking to PO Lines needs to be more robust including the ability to link to closed/cancelled orders; the ability to link to multiple orders and the display of linked orders in its own tab in the license display | 2015 H2 | I believe we can link to a closed order and we do have the tab of linked orders, but we can't yet link to cancelled orders (unless we reopen them) and I believe the multiple order linking is only for 2? And we still can't link to physical orders! | Delivered Nov 2015, Please submit a SFC or include SFC
There should be the ability to locally define statuses to support local naming conventions and workflows | Released as part of March 2015 release | now working as needed
The license summary tab needs another field for the second party’s signature information | Released as part of March 2015 release | now working as needed
We should be able to add extra, locally-defined fields, as needed, to the summary tab | Requires additional analysis | We will continue to lobby for this through NERS & Idea Exchange. | Currently not planned
Availability of an additional coloured symbol (or another indicator) added at the top level of a license that will indicate if a note has been added to a license amendment. (p. 8 of report) |  | As a usability issue, this should be consistent across all areas of Alma. We shouldn't have to train staff that the blue tab only works in certain areas of the system. | Currently not planned
Workflows
Alma needs workflows for licensing that will allow the tracking of the entire life cycle of the license | Released as part of March 2015 release | We don't consider that what they've done actually has created a "workflow" - there's still no way to track the license through the process nor to assign various steps to other people. The work around is to use the activation checklist - and since licensing predates activation in most cases, this is really not an appropriate workaround for some organizations. | Currently not planned to change - will be taken under consideration
License start date should not be a required field. | Released as part of March 2015 release | This is still not fixed. A start date is still required for any license and if you don't enter one the system defaults to today's date. | Please submit a SFC or include SFC | NU: #00237214 Plymouth: 00060541
Licenses need to be part of the physical resources | Requires additional analysis | We will continue to lobby for this through NERS & Idea Exchange. | Currently not planned | Plymouth: 55865 & 76593
Alma should be able to distinguish between different license types | Requires additional analysis | We will continue to lobby for this through NERS & Idea Exchange. | Currently not planned
Alma should make license records interoperable with Group Settings for electronic inventory. | Planned for 2017 | Still pending | Planned for 2017 |  | This functionality is still tentativley planned for 2017
Terms
Ex Libris needs to continue to add DLF/ERMI terms to Alma with the goal of offering the entire data set | Ongoing | Still pending | ongoing
There must be support for the addition of locally defined terms both to cover license terms that have come to the fore since DLF/ERMI was written and to allow for local and international issues not covered by DLF/ERMI | 2015 H2 | We are able to add new fields but the display to Primo functionality is "broken". The response to the Case indicated it would be fixed in the 2nd quarter of 2016. | Please provide the SFC | NU: #00167755
More flexibility and control is needed in license terms’ discoverability including more control over the mapping table and the Primo display. | Not Clear | We will continue to lobby for this through NERS & Idea Exchange. | More information is needed
License term display needs to be developed to work with other information delivery systems than Primo | Mash-up for 3rd part discovery system will include license information | Still pending? We've not heard from any sites that are using anything but Primo. | 3rd party discovery systems use Alma Link resolver mash up which include license information
Functionality
The ability to add terms and reorder terms using configuration should be more stable and easier to update. It should NOT be based on numbers that can easily be duplicated | Requires additional analysis | We will continue to lobby for this through NERS & Idea Exchange. | Currently not planned
The authorized user functionality in Acquisitions/Configuration should be linked to licenses to allow us to consistently populate an authorized user field with information that corresponds to other authorized user information related to a specific license allowance | Requires additional analysis |  | currently not planned - will be taken under consideration
There must be a read-only role for licenses to allow for the broad sharing of license information but also allowing for the protection of the integrity of the license as a “document of record”. | 2016 | Still pending | Planned for 2016 |  | This functionality is depended on a broader development to enable read only adminstrator capability and such will developed in 2017
It should be possible to create locally controlled lists of vocabulary to populate the various terms fields, allowing for consistency in display and accuracy of data retrieval | Tentativley planned for 2017 | Still pending | Planned for 2017 |  | Tentativley planned for 2017
To support future migration and/or repurposing of license data. Alma should continue to support relevant standards that allow for mark-up and structuring of license data | Ongoing | Ongoing? | Alma Supports DLF, there are no plans to support additional standards within Alma. Alma does support loading ONIX-PL licenses which are converted to DLF attributes
License Code: Make searchable/browsable index. If the beginning of a search is correct, the user will be presented a browsable index and be able to choose records nearby. (p. 15 of report) |  | We will continue to lobby for this through NERS & Idea Exchange. | No plans for browsable index
Add “Licenses” as one of the search categories from the main, persistent Alma search box. (p. 15 of report) |  |  | Planned for 2017
Alma must be able to prompt for renewals in due time. (p. 15 of report) |  |  | Planned for 2017
What are the plans in the "network zone" for the sharing of licenses? There needs to be functionality allowing the centralized posting of a consortial license that then can be linked to by other member libraries. (p. 16 of the report) |  |  | In the context of Alma Collaborative Network Alma allows defining a license of type Negotiation in the Network Zone. Negotiation license includes license terms and content negotiated by the central office for the consortia members. Central office can share the license with the relevant members
Template records which can be copied and updated to fit the particular resource/date/etc. (p. 16 of report) |  |  | Planned for 2017
"Historical License" information should be "inherited" by portfolios/should be viewable at the portfolio level & thus more than one license can be associated with a portfolio (p. 16 of report) |  | We were given some historical license tracking functionality but it's "unforgiving" in that it can't be edited/deleted if a mistake is made. | Planned for 2017
The "all" filter is not really "all" licenses. It doesn't include "deleted" licenses (which really needs to be renamed to suppressed or something similar). "All" should be "all" and a filter for "active & draft" should be added. (p. 17 of the report) |  |  | Planned for 2016
Support for ONIX-PL licenses (p. 17 of the report) |  | It is possible to load an ONIX-PL license but the fields that actually come in are limited and not always the most pertinent. | planned to improve in 2016
Analytics & Reporting
Licenses should be supported in Analytics allowing the reporting out of license information as well as reports that link license information to payment and inventory information | Tentatively planned for 2017 | Still pending | Planned for 2016 |  | Tentativley planned for 2017
We must be able to query licenses using set functionality to allow us to pull out licenses that meet certain criteria or which contain certain licensing terms. | Tentatively planned for 2017 | Still pending | Planned for 2016 |  | Tentativley planned for 2017
We should be able to export any of the license tabs using the “Tools” function | Long term road map | What is wanted is the ability to export as a spreadsheet so that the data can be repurposed, as we do with other areas of Alma. | Plans to include a print version of the License Planned for 2017 |  | Loang term road map